## CETM 46 - assignment 1
GANTT CHART | [6 empty] | Smartsheet Tip ➜ | [7 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | CETM 46 - Assignment 1 |  |  |  |  | COMPANY NAME | [10 empty] | University of Sunderland
PROJECT MANAGER |  | Penny CHAN |  |  |  |  | DATE | [10 empty] | 2020-05-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [20 empty] | PHASE TWO
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Report Initiation
1.1 | Topic identification | Penny CHAN | 2020-05-15 | 2020-05-18 | 3 | 100% | bar: WEEK 1 F to WEEK 2 S
1.2 | Problem identification and potential solution | Penny CHAN | 2020-05-18 | 2020-05-24 | 6 | 100%
1.3 | Comparative analysis with current solution in market | Penny CHAN | 2020-05-22 | 2020-05-29 | 7 | 60% | bar: WEEK 2 M to WEEK 3 F
1.4 | Objective setting | Penny CHAN | 2020-05-29 | 2020-05-31 | 2 | 0% | bar: WEEK 3 F to WEEK 3 S
1.5 | Scope and deliverable | Penny CHAN | 2020-05-29 | 2020-05-31 | 2 | 0% | bar: WEEK 3 F to WEEK 3 S
2 | Feasibility Study
2.1 | Dataset collection | Penny CHAN | 2020-05-18 | 2020-05-27 | 9 | 70% | bar: WEEK 2 M to WEEK 3 W
2.2 | Dataset review and cleaning | Penny CHAN | 2020-05-27 | 2020-05-31 | 4 | 50% | bar: WEEK 3 W to WEEK 3 S
2.3 | Literature review on software engineering methodology, machine learning models, software development tools/platforms | Penny CHAN | 2020-05-31 | 2020-06-09 | 9 | 0% | bar: WEEK 3 S to WEEK 6 T
2.4 | Insight and Conclusion | Penny CHAN | 2020-06-09 | 2020-06-11 | 2 | 0% | bar: WEEK 6 T to WEEK 6 S